## Sheet1
Weeks | PLAN START | PLAN DURATION(in weeks) | EXTRA DURATION TAKEN(in weeks) | PERCENT COMPLETE
1 | Team introduction and registering to github repository | 1 | 1 | 100%
2 | Understanding case study and creating usestories | 1 | 1 | 100%
3 | Creating Usecase diagram | 1 | 1.5 | 50%
4 | Designing UserInterface and database | 1 | 1 | 50%
5 | Designing and developing Login userstories | 1 | 1.5 | 85%
6 | create Register Patient userstories and start designing appointment, staff userstories | 1 | 1.5 | 85%
7 | Coding on Appointments, Staffs and test result Userstories | 1 | 1 | 50%
8 | continuation on coding appointment, staff and testresults | 1 | 2 | 60%
9 | coding on prescription and class diagram | 1 | 1 | 85%
10 | Code enhancement and testing | 1 | 1 | 100%
11 | Testing and bug fixing | 1 | 1 | 60%
12 | Presentation | 1 | 0 | 100%